| Timeline | Action |
| --- | --- |
| CEDAW 79th session, June 2021 | Day of General Discussion on indigenous women and girls |
| CEDAW 80th session, October-November 2021 | Expert group meeting online, or in case the COVID-19 situation allows, in Geneva |
| September 2021 –December 2021 | Regional consultations online, or in case the COVID-19 allows, in-person meetings in Africa (location tbc), the Americas(location tbc), Asia-Pacific Region (location tbc) and Europe and Central Asia (location tbc) |
| March – April 2022 (for 6 week) | Posting the advanced draft GR on the public website of OHCHR for the GR for comments by stakeholders |
| CEDAW 82th session, June-July 2022 | First reading of the draft GR in plenary |
| CEDAW 83th session, October – November 2022 | Second reading of the draft GR & adoption by the Committee |